## Risk register
Project Risk Register Template
Log project risks with probability, impact, a calculated risk score, an owner and a mitigation plan.
Scoring | Probability and impact from 1 (low) to 5 (high). Score = probability × impact.
ID | Risk description | Category | Probability (1–5) | Impact (1–5) | Score | Owner | Mitigation plan | Status
R-01 | Key vendor contract not renewed before go-live | Commercial | 3 | 5 |  | Programme manager | Start renewal 90 days early; identify fallback vendor | Mitigating
R-02 | QA capacity reduced in Sprint 15 due to leave | Resourcing | 4 | 3 |  | Scrum master | Pull test automation forward; borrow QA from team B | Open
R-03 | Third-party API rate limits during peak | Technical | 2 | 4 |  | Tech lead | Add caching and back-off; agree higher limit with provider | Open
R-04 | Data migration takes longer than planned | Schedule | 3 | 4 |  | Data lead | Run two rehearsals; migrate historic data after launch | Open
R-05 | New security requirement from compliance review | Compliance | 2 | 3 |  | Product owner | Book review early; reserve buffer in Sprint 16 | Closed
Run this in Taskmei: https://www.taskmei.com/register