## RACI matrix
RACI Matrix Template
Clarify who is Responsible, Accountable, Consulted and Informed for each recurring activity on an agile project.
Legend | R = Responsible, A = Accountable, C = Consulted, I = Informed
Activity | Product Owner | Scrum Master | Developers | QA | Stakeholders
Maintain and prioritise the product backlog | A/R | C | C | C | I
Refine and estimate backlog items | A | C | R | C | -
Sprint planning | R | A | R | R | I
Daily stand-up | I | A | R | R | -
Build and test increment | C | I | A/R | R | -
Sprint review and demo | A | R | R | R | C
Retrospective and improvement actions | C | A/R | R | R | -
Release to production | A | I | R | R | I
Track and mitigate risks | C | A | C | C | I
Run this in Taskmei: https://www.taskmei.com/register