## Sprint planning
Sprint Planning Template
Plan a sprint on one page: the sprint goal, the team's capacity and the backlog items the team commits to.
Sprint | Sprint 14
Sprint goal | Customers can reset their password without contacting support
Dates | 13 Oct – 24 Oct 2026 (10 working days)
Team capacity | 155 focused hours / about 29 story points
Committed | 29 story points
ID | Backlog item | Type | Story points | Priority | Owner | Acceptance criteria (summary) | Status
TM-142 | Request a password reset link by email | Story | 5 | High | Asha | Link sent within 2 min; same message for unknown emails | To Do
TM-143 | Set a new password from the reset link | Story | 5 | High | Ravi | Link single-use, expires after 24 h; password rules enforced | To Do
TM-144 | Email confirmation after password change | Story | 3 | Medium | Meera | Confirmation sent; includes 'not you?' support link | To Do
TM-151 | Login fails on Safari 17 | Bug | 3 | High | Ravi | Login works on Safari 17 desktop and iOS | To Do
TM-152 | Evaluate rate limiting for reset requests | Spike | 2 | Medium | Asha | Recommendation documented with chosen approach | To Do
TM-153 | Automated tests for reset flow | Task | 8 | Medium | QA | End-to-end tests cover happy path and expiry | To Do
TM-154 | Update help-centre article | Task | 3 | Low | Meera | Article reviewed and published | To Do
Run this in Taskmei: https://www.taskmei.com/register